## Sheet1
PROJECT LOGS
Date (YYYY-MM-DD) | Member | Details
2023-06-30 | Olumayowa, Shivani, Rafaeat, Paulo | Defining communication protocols, project managing format and version control (Git)
2023-06-30 | Shivani | Setup GitHub for the project
2023-07-04 | Shivani, Rafaeat | Workshop about GitHub and defining procedures for coding updates
2023-07-07 | Olumayowa, Shivani, Rafaeat, Paulo | Defining Topic: Electronics Renting Platform
2023-07-07 | Olumayowa | Defining project description: An electronics renting platform for which primarily target audience are students who can rent gadgets and stuffs from other users (including from their own instutes.
2023-07-11 | Paulo, Olumayowa, Rafaeat, Shivani | Drafts the site map,Disscused the page contents
2023-07-13 | Paulo | Designing the site map with draw io,
2023-07-13 | Olumayowa | Wireframe draft: About Us
2023-07-13 | Paulo | Wireframe draft: Place Order, Contact
2023-07-13 | Rafaeat | Wireframe draft: Home, Profile
2023-07-13 | Shivani | Wireframe draft: Product List, Product Detail
2023-07-13 | Everybody | Deciding the color scheme
2023-07-13 | Rafaeat | Logo Design, Template Development, Partial Homepage development
2023-07-14 | Paulo | Initialization of the Contact Us page development
2023-07-14 | Rafaeat | Created and added the favicon
2023-07-15 | Shivani | Created card for products list
2023-07-17 | Shivani | Added owner and product images and created product list
2023-07-18 | Paulo | Submited the first version of the contact_us page code
2023-07-20 | Shivani | Merged the rough code to development
2023-07-20 | Mayowa | Created About Page, Working on adding social links on the footer
2023-07-15 | Rafaeat | Profile page design, Resizing the images
2023-07-17 | Rafaeat | Navigation for mobile
2023-07-18 | Rafaeat | Combined all pages navigation link on all pages
2023-07-20 | Rafaeat | Design updates in about_us page
2023-07-20 | Mayowa | Added the news letter, Contact Us and subscription at the end of the body
2023-07-22 | Shivani | Fixed and added full product list
2023-07-22 | Shivani | Added load more button and pushed the code to development and fixed css conflicts
2023-07-24 | Shivani | Worked on Product detail page partially
2023-07-26 | Shivani | Worked on Product detail page, added description and other content
2023-07-27 | Shivani | Pushed Product Detail code to development and fixed css conflicts
2023-07-27 | Paulo | Applying forms validation, minor adjustments, and documentation on place order (checkout) page and contact us page
2023-07-27 | Mayowa | Applied main picture to the About Page
2023-07-27 | Mayowa | Applied css comments on both the CSS and HTML, adjusted the footer links
2023-07-28 | Shivani, Rafaeat | compling and re organising the files
2023-07-28 | Shivani, Rafaeat | Reviewing home page after merging
2023-07-29 | Mayowa | Reviewing About Page after merging
2023-07-30 | Rafeat | Reviewing Home Page, Category and Profile page after merging
2023-07-31 | Shivani | Removing all CSS, HTML and reviewing the product and product list after merging
2023-07-01 | Paulo | Reviewing the Checkout page and contact Us page after merging
2023-08-03 | Shivani | Documentation, Titles and Fav icons for all pages, Prepared "other" folder
2023-08-04 | Rafaeat | Adding some final comments
2023-08-04 | Mayowa, Shivani, Rafeat, Paulo | Meeting for final submission and plan for presentation format